## Back End
Back end
| Task | Hours (h) | Question
1 | Add, Edit Customer info | 8
- create model db - API add, edit.
2 | Send data to Finance Company | 2 | Chua co API SHB
3 | Export API to recieve update from Finance Company | 2 | temp data from FC -> Thanh
4 | Notification to device | 24
5 | Update data to CRM | 4 | temp data API info of CRM -> Toan Thang account
6 | API get otential customer (to app) by user id - APP call API to get potential customer | 2 | Missing screen display new data -> Thanh
7 | Export API save potential customer from CRM - CRM have potential customer -> call to HUB to send all - HUB recieve and update to DB | 4
8 | API login | 2
9 | API logout | 0
10 | API get total customer info | 2
11 | API get customer info by id | 2
12 | API get list customer by status | 2
13 | API upload img | 8
14 | API check version | 2
| Sum | 64

## Mobile
Mobile
| Task | Hours (h) | Question
1 | Notification - recieve message - click navigate to specific screen | 24 | - separate 3 screen: home, notification, side menu(log out) - Notification: online, offline, kill app
2 | Login - request token ( send UUD for iOS) - if server reviece wrong token => auto logout | 8
3 | Side menu | 8
4 | Screen Home | 4
5 | Screen Tin chap | 4
6 | Screen Green A | 8
7 | Screen Add customer | 32
8 | Screen List customer info has status reject | 8
9 | Screen draft customer info | 8
10 | Screen All customer info | 8
11 | Screen Check duplicate - cmnd - ma KH - Driver lince - warranting contract | 18
12 | Screen check CAT | 4
13 | Screen calculator loan | 8
14 | Screen expired loan | 4
15 | Screen detail expired loan | 4